## DetailedSchedule
Detailed Schedule
|  | Development Plan | Test and Demonstration Plan
Feb | 7 | • Set up Database model | • Test database with sample entries
| 14 | • Database classes • Employee class • Incident class • Room class • Group class • GUI classes | • Test database classes by using defined methods in the class • Show interactivity between classes by pulling information from other classes
| 21 | • Begin implemention of Clean List generation | • Generate list of rooms that need to be cleaned • Test with all rooms needing cleaned, mix of rooms clean and dirty, and all already cleaned.
| 28 | • Begin implemention of Cleaning Assignment List generation • Continue implementation of Clean List • Start development of Web and Android application | • Continue with last weeks tests • Attempt to assign rooms to Employees • Can not have a room assigned more than once
March | 7 | • Begin implemenation of Incident tracking & reporting • Continue Cleaning Assignment List implementation • Finish implementation of Clean List • Login-screen for Android and Web Apps • Register screen for Android and Web Apps | • Continue with last weeks tests • Attempt to report an incident and make sure appropriate notifications are sent. •Attempt to register both a Manager and an Employee •Attempt to login with an authenticated user •Test login screen redirection based on user-level
| 14 | • Incident reporting through GUI • Begin Incident List Implemenation • Continue implemenation of incident tracking and reporting • Finish Cleaning Assingment List implementation • Home screen for Android and Web Apps | • Attempt to create Cleaning assignment from a Manager account • Access a Cleaning Assignment List from an Employee perspective
| 21 | • Begin implementing Wake-up Call functionality • Continue Incident List implementation • Finish Incident tracking & reporting • Pull Incident List through GUI | • Test a new Incident • Test updating an incident • Test Resolving an Incident
| 28 | • Begin implementing Departing Customer List • Continue Wake-up Call implemenation • Finish Incident List tracking & reporting • Room List screen for Android and Web Apps | • Continue with previous weeks tests • Test for Residual Fault
Apr | 4 | • Begin Assignment History implementation • Continue Departing Customer List implementation • Finish Wake-up Call implemenation • Room screen for web and android | • Test creating a wake-up call • Test getting a Wake-Up Call List • Produce notification for Rooms designated with having a wake-up call
| 11 | • Continue Assignment History implementation • Finish Departing Customer List implementation • Android and Web App full integration | • Test for residual faults • Test generation of list of guests leaving • Attempt to save Employee and Room IDs associated with the date
| 18 | • Finish Assignment History implementation • Continue Android and Web Apps | •Test Complete Employee Functionality
| 25 | • Finish Android and Web Apps • Handle any last minute issues. | •Test Complete Manager Functionality

## GanttChart
Gantt Chart
| February |  |  |  | March |  |  |  | April
| 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25
Set-up Database
Create Object Classes
Create GUI Classes
Clean List and Associated Functionality
Cleaning Assignment List and Associated Functionality
Incident Implementation
Incident List and Associated Implementation
Inspect List and Associated Implementation
Wake-Up Call List and Associated Implementation
Departing Customer List and Associated Implementation
Assignment History
Web Application Front-End Development